## Slide 1: Northwind Freight × Relay: onboarding kickoff
Fictional sample · Customer onboarding deck and adoption plan
Kickoff call, 12 January · 120 seats across dispatch and finance
Notes: Everything in this deck is fictional: Relay is an invented workflow-automation product and Northwind Freight is an invented customer. Open with introductions from both sides and their roles. Purpose of the call: agree goals, what 'live' means, owners and dates, and how progress will be measured.

## Slide 2: Goals, in Northwind's words
From the sales handoff; confirmed by Dana Ortiz (Ops Director, sponsor) at kickoff
Dispatch logs all delivery exceptions in Relay instead of the shared spreadsheet
Finance receives an automated weekly exceptions report
The exceptions spreadsheet is retired by the end of onboarding
Notes: Read each goal back and ask Dana to correct the wording live. If a goal changes, update this slide in the meeting and record it in the notes. These goals drive the definition of done on the next slide.

## Slide 3: Definition of done
Onboarding is complete when all three conditions are true
100 of 120 seats activated (as defined in the metric dictionary)
Exceptions spreadsheet set to read-only, signed off by the customer project lead
Weekly finance report delivered automatically for 3 consecutive weeks
Notes: Each condition is observable and has a source: the admin console for seats, written sponsor sign-off for the spreadsheet, and the report delivery log for finance. Ask whether 100 seats is the right threshold; the remaining 20 seats may be occasional users.

## Slide 4: Milestone plan: setup
One named owner per side on every milestone
Milestone | Date | Northwind / Relay owner | Exit criterion
1. Kickoff, goals confirmed | 12 Jan | Dana Ortiz / Sam Lee | Goals signed off in notes
2. SSO and admin setup | 16 Jan | Priya Shah / Alex Kim | Admin logs in through SSO
3. TMS integration | 23 Jan | Priya Shah / Alex Kim | Test exception syncs end to end
4. Dispatch training (2 sessions) | 28 Jan | Marco Ruiz / Sam Lee | Both held; recording shared
Notes: Owners: Dana Ortiz (Ops Director, sponsor), Priya Shah (IT), Marco Ruiz (Dispatch lead) at Northwind; Sam Lee (CSM) and Alex Kim (Implementation) at Relay. If anyone cannot commit to their date, change it now rather than after it slips.

## Slide 5: Milestone plan: go-live
Spreadsheet retirement depends on milestones 1 to 5
Milestone | Date | Northwind / Relay owner | Exit criterion
5. Finance report configured | 30 Jan | Jo Patel / Alex Kim | First automated report received
6. Spreadsheet read-only | 13 Feb | Dana Ortiz / Sam Lee | Sponsor confirms in writing
7. Onboarding close review | 27 Feb | Dana Ortiz / Sam Lee | Done met, or gaps assigned
Notes: Jo Patel is Northwind's finance manager. Milestone 6 is the one most likely to slip, because it needs dispatch to stop using the spreadsheet. The weekly reviews track spreadsheet displacement so we see the risk early.

## Slide 6: Metric dictionary: activation and usage
Same definitions in every review
Metric | Formula | Source
Seats activated | Activated users ÷ licensed seats | Admin console
Weekly active users (WAU) | Distinct users with 1+ exception or report view, last 7 days | Event log
WAU rate | WAU ÷ licensed seats | Derived
Notes: Activated means logged in at least once and completed profile setup. WAU counts activated users with at least one logged exception or report view in the last 7 days. Every review slide states its time window, for example 'WAU, week ending 6 Feb'. Review weekly during onboarding.

## Slide 7: Metric dictionary: outcomes
Customer-supplied figures are labelled as such
Metric | Formula | Source
Core action volume | Exceptions logged in Relay per week | Event log
Spreadsheet displacement | Relay ÷ (Relay + spreadsheet) exceptions | Event log + Northwind row count
Time to first value | First automated report date − contract start | CSM milestone log
Notes: The spreadsheet row count comes from Northwind (Marco Ruiz), not from Relay, so it is labelled as customer-supplied. No benchmark targets are shown: targets are set for this customer from the goals and definition of done.

## Slide 8: Adoption review: week ending 6 Feb
Fictional data · formulas from the metric dictionary
Metric | W/e 30 Jan | W/e 6 Feb
Seats activated | 71 / 120 (59%) | 94 / 120 (78%)
WAU rate | 58 / 120 (48%) | 77 / 120 (64%)
Relay exceptions logged | 310 | 402
Spreadsheet exceptions (Northwind count) | 140 | 61
Spreadsheet displacement | 69% | 87%
Notes: Check the arithmetic: displacement 310 ÷ (310 + 140) = 310 ÷ 450 = 68.9%; 402 ÷ 463 = 86.8%. WAU rate 77 ÷ 120 = 64.2%. Finance activated after the report was set up, which explains most of the seat increase. Spreadsheet counts supplied by Marco Ruiz.

## Slide 9: What the review tells us
Read-only on 13 Feb looks achievable if activation continues
6
More seats needed
94 of 100-seat target; 26 seats still inactive
87%
Spreadsheet displacement
Up from 69% the week before
13 Feb
Read-only milestone
On track, owner Dana Ortiz
Notes: State the conclusion, not just the numbers: activation is behind the 100-seat target (94 of 100), displacement is rising, and the read-only milestone is achievable if at least 6 of the 26 inactive seats activate before 13 Feb.

## Slide 10: Blockers and asks
Northwind (Marco Ruiz): share the list of the 26 dispatch and finance users not yet activated
Relay (Sam Lee): follow up with each inactive user and offer a short catch-up session
Both sponsors: confirm the 13 Feb read-only date or agree a new one now
Notes: Each ask has one owner. If the read-only date moves, the close review on 27 Feb may move too; agree that in this meeting rather than by email afterwards.

## Slide 11: Next milestone: spreadsheet read-only, 13 Feb
Owners: Dana Ortiz (Northwind) and Sam Lee (Relay)
Next adoption review: week ending 13 Feb · Fictional sample
Notes: Close by restating the next milestone, the owners and the date of the next review. Send the exported deck and meeting notes to both teams after the call.