## Slide 1: Project Willow Overview
Introducing the 60-day inventory pilot at 8 fictional stores.
Notes: Introduce the pilot project and its significance.

## Slide 2: Pilot Budget and Measurement
$48,000
Budget Ceiling
60 days
Pilot Duration
Notes: Discuss the budget constraints and measurement strategy.

## Slide 3: Delivery Plan Timeline
1
Weeks 1-2
Record baseline and confirm store owners.
2
Weeks 3-6
Run replenishment checks.
3
Weeks 7-8
Review stockouts and report findings.
Notes: Outline the step-by-step plan for the pilot.

## Slide 4: Risks and Mitigation
Incomplete store logs could weaken comparison.
Jordan Vale to review missing entries weekly.
Notes: Highlight potential risks and mitigation strategies.

## Slide 5: Approval Request
Approve the 60-day inventory pilot by November 20, 2026. Contact Jordan Vale for further details.
Notes: Conclude with the decision request for pilot approval.