## Slide 1: Approve the Project Willow pilot
Fictional example · manually authored
60 days · 8 stores · proposed ceiling $48,000
Notes: Manually authored from project-willow.docx. Fictional example. Not AI-generated.

## Slide 2: Define the decision
COO and finance lead: approve the scope and budget.
Approval requested by November 20, 2026.
Owner: Jordan Vale, operations lead.
Notes: Manually authored from project-willow.docx. Fictional example. Not AI-generated.

## Slide 3: Measure before claiming a result
No improvement has been measured.
Record a two-week stockout baseline.
Track stockouts weekly during the pilot.
The $48,000 ceiling is proposed, not reported spend.
Notes: Manually authored from project-willow.docx. Fictional example. Not AI-generated.

## Slide 4: Run the eight-week plan
Weeks 1–2: record baseline; confirm store owners.
Weeks 3–6: run replenishment checks.
Weeks 7–8: review stockouts and report findings.
Notes: Manually authored from project-willow.docx. Fictional example. Not AI-generated.

## Slide 5: Approve scope, then return with findings
Fictional training example; no customer results.
Incomplete logs could weaken the comparison. Jordan Vale reviews missing entries weekly.
Notes: Manually authored from project-willow.docx. Fictional example. Not AI-generated.