# Project Willow: inventory pilot

Fictional training example. All names, amounts and dates are invented; no customer results.

# Decision requested

Approve a 60-day inventory pilot at 8 fictional stores. Approval is requested by November 20, 2026. Owner: Jordan Vale, operations lead.

# Budget and measurement

The proposed budget ceiling is $48,000. No improvement has been measured. Track stockouts weekly against a two-week baseline; do not state a savings forecast as a result.

# Delivery plan

Weeks 1-2: record baseline and confirm store owners. Weeks 3-6: run replenishment checks. Weeks 7-8: review stockouts and report findings.

# Risks and approval

Incomplete store logs could weaken comparison. Jordan Vale will review missing entries weekly. Ask the COO and finance lead to approve the scope and budget; return with findings after the pilot.